## BugReport
Bug ID | Title | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Status
BUG-TC03 | Empty Prompt Generates Unexpected Image | When the prompt is empty and "Generate" is clicked, the system generates an unrelated image | 1. Leave prompt empty 2. Click Generate | Error message or disabled button should appear | System displays an unrelated image | High | Open
BUG-TC06 | Second Prompt Combines Content from First | Multiple generations mix content from different prompts | 1. Enter prompt: “A cat wearing sunglasses” 2. Click Generate 3. Enter prompt: “Space landscape at night” 4. Click Generate | Each prompt generates unique image | The second image contains both cat and space | High | Open
BUG-TC07 | Invalid Characters Not Handled Properly | Invalid characters like “!!!!!!!” are processed and generate incorrect images | 1. Enter “!!!!!!!” 2. Click Generate | Error shown or no image generated | System generated unrelated image | Medium | Open
BUG-TC09 | Mobile Layout Partially Broken | Some UI components overlap on small mobile screens | 1. Open site on phone (e.g., Samsung A23) 2. Enter prompt and generate | Responsive layout, no overlaps, everything aligned | Some buttons overlapped, layout not fully responsive | Medium | Open
BUG-TC11 | Arabic Prompts Misinterpreted | Arabic input results in incorrect or unrelated image | 1. Enter “قطة على السطح” 2. Click Generate | Image reflects Arabic prompt | Generated image unrelated to Arabic prompt | Medium | Open
BUG-TC13 | NSFW Filter Inconsistent | Violent prompts bypass NSFW filter while nudity is blocked | 1. Enter nudity-related prompt 2. Enter violence-related prompt 3. Click Generate on both | Both should be blocked | Only nudity blocked, violent image generated | High | Open
BUG-TC16 | Prompt History Not Working | Previously entered prompts not saved or visible | 1. Enter prompt 1 2. Click Generate 3. Enter prompt 2 4. Click Generate 5. Check prompt history | All prompts saved and displayed | No prompt history shown | Low | Open
BUG-TC19 | Session Data Lost on Refresh | Last prompt/image disappears after refreshing | 1. Enter prompt 2. Click Generate 3. Refresh page | Last prompt/image remains visible | Page reloads with all data cleared | Medium | Open
BUG-TC21 | Remove Image Fails | Clicking remove does not delete generated image | 1. Generate image 2. Click "Remove" | The image should disappear | Image remains on screen | Medium | Open
BUG-TC22 | Share Feature Broken | Clicking Share does nothing or shows error | 1. Generate image 2. Click "Share" | Share link or modal should appear | Error or no response shown | Medium | Open